## Sprint Schedule
Date | Schedule | Deliverable
2017-09-27 | Sprint 1 | Initial Setup and Planning
2017-10-04 |  | Front-End Planning and Wireframes
2017-10-11 | Sprint 2 | Front-End UI/UX Development and User Authentication System (UI)
2017-10-18 | First Demo | Creating a Powerpoint regarding all the basic functionalities that have been implemented and explain them
2017-10-25 | Sprint 3 | Back-End API Setup, Payment Gateway Integration(API), Database Implementation
2017-11-01 | Second Demo | 10 slide powerpoint and a demo of the actual application
2017-11-08 | Sprint 4 | Unit Testing and Debugging(Full Stack) and Deployment
2017-11-15 | Prototype Demo | Demonstrating core functionalities such as product listings, user registration, and checkout process.
No class
2017-11-29 | Sprint 6
2017-12-06 | Final Demo | Deliver a comprehensive final demo showcasing all implemented features of the e-commerce marketplace
2017-12-13 | Final Project Due | Give one line answer for final demo following above instructions